## Progress Claim
PROGRESS PAYMENT CLAIM
Builder to Client Progress Claim - NZS 3910 / Standard Building Contract
Claim Number: | PC-006 |  | Claim Date: | 14/07/2026 |  | Contract Number: | BC-2026-014
Builder: | Kauri Build Ltd |  | NZBN: | 9429046123458 |  | GST Number: | 112-233-445
Client: | Hemi and Aroha Ngata |  | Site Address: | 24 Totara Grove, Tauranga
Contract Value (excl GST): | 350000 |  | Retention Rate: | 10%
Item No | Description of Works | Contract Value (excl GST) | % Complete to Date | Value Completed to Date | Previous Claims ($) | This Claim (before retention) | Retention Held ($) | Net Claim This Period | Status
1 | Site Preliminaries & Set-up | 15000 | 100% |  | 10000
2 | Foundations & Groundworks | 45000 | 100% |  | 31500
3 | Framing & Structure | 60000 | 100% |  | 42000
4 | Roofing | 35000 | 80% |  | 20000
5 | External Cladding & Weatherproofing | 55000 | 60% |  | 16500
6 | Plumbing Rough-in | 30000 | 50% |  | 10500
7 | Electrical Rough-in | 25000 | 40% |  | 7000
8 | Interior Linings & Insulation | 50000 | 20% |  | 0
9 | Painting & Decorating | 20000 | 0% |  | 0
10 | Landscaping & Final Clean | 15000 | 0% |  | 0
TOTALS
Subtotal - Net Claim This Period (excl GST):
GST @ 15%:
TOTAL CLAIM AMOUNT PAYABLE (incl GST):
Overall Contract % Complete:
Items Marked Complete:
[7 empty] | Payment Due (20 working days): | Refer to contract terms

## Summary Dashboard
PROGRESS CLAIM - SUMMARY DASHBOARD
Key metrics automatically calculated from the Progress Claim sheet
Total Contract Value (excl GST):
Total Value Completed to Date:
Total Previous Claims:
This Claim (before retention):
Total Retention Held:
Net Claim This Period (excl GST):
GST @ 15%:
TOTAL AMOUNT PAYABLE (incl GST):
Overall Contract % Complete:
Remaining Contract Value:
Look up item description: | Roofing
Value Completed to Date ($):
Description of Works | % Complete | Value Completed
Contract Value Breakdown | Amount
Previous Claims
This Claim (Net)
Remaining Contract Value

## Instructions
INSTRUCTIONS - BUILDER PROGRESS PAYMENT CLAIM
Sheet | Purpose and Notes
Progress Claim | Main claim sheet. Enter claim number, date, contract number, builder and client details, total contract value and retention rate in the pale yellow input cells. Update the '% Complete to Date' and 'Previous Claims' columns each claim period - all other columns (Value Completed, This Claim, Retention Held, Net Claim, Status, GST and Total Payable) calculate automatically. The Status column uses an IF formula and is colour-coded by conditional formatting (green = Complete, grey = Not Started, red = negative claim value).
Summary Dashboard | Read-only overview pulling live figures from the Progress Claim sheet using direct cell references, VLOOKUP and COUNTIF-style formulas. Includes bar charts showing percentage complete and value completed by trade, and a pie chart showing how the contract value is split between previous claims, this period's net claim and remaining contract value. Use the item lookup box to check the value completed for any specific trade.
Instructions | This guide. Explains the purpose of each sheet and how to use the workbook correctly.
General Notes
- All amounts are in New Zealand dollars (NZD) and exclude GST unless stated otherwise.
- GST is calculated at the current rate of 15%.
- Retention is typically held at 5-10% of each progress claim until practical completion and the end of the defects liability period, per standard NZ building contracts.
- Ensure the Builder's NZBN and GST number are correct before issuing a claim to the client.
- Payment terms should follow the timeframes set out in the signed building contract.