## Renovation Budget
Home Renovation Budget - Aotearoa New Zealand
Property Address: 24 Totara Grove, Hamilton
Category | Room/Area | Item Description | Contractor | Budgeted Cost | Actual Cost | Variance | % of Total Budget | Status | Date Completed
Kitchen | Kitchen | Full cabinetry replacement and benchtop | Aroha Build Co | 18500 | 19250 |  |  | Complete | 05/02/2026
Bathroom | Main Bathroom | Retile and new vanity unit | Hemi Plumbing Ltd | 9500 | 8950 |  |  | Complete | 18/02/2026
Flooring | Living Areas | Engineered timber flooring | Manaia Flooring Co | 7200 | 7600 |  |  | Complete | 02/03/2026
Painting | Whole House | Interior and exterior repaint | Liam Painters | 6400 | 6100 |  |  | Complete | 20/03/2026
Roofing | Roof | Reroof with Colorsteel | Charlotte Roofing NZ | 15800 | 16400 |  |  | Complete | 10/04/2026
Landscaping | Backyard | Deck extension and garden beds | Sophie Landscapes | 8900 | 0 |  |  | Not Started
Electrical | Whole House | Rewiring and new switchboard | Tane Electrical Ltd | 5200 | 5300 |  |  | Complete | 28/03/2026
Plumbing | Kitchen & Bathroom | New pipework and fittings | Hemi Plumbing Ltd | 4100 | 3950 |  |  | Complete | 15/02/2026
Windows | Whole House | Double glazed window upgrade | Nikau Windows Co | 11200 | 0 |  |  | In Progress
Deck | Outdoor | New deck and pergola | Sophie Landscapes | 6800 | 0 |  |  | In Progress
TOTAL
Overspend Items |  | Under Budget Items |  | Items Not Started

## Contractor Payments
Contractor Payments and Invoices
Contractor | Trade | NZBN | Invoice No. | Invoice Date | Amount (excl. GST) | GST (15%) | Total (incl. GST) | Paid Date | Payment Status
Aroha Build Co | Carpentry | 9429041234567 | INV-1042 | 01/02/2026 | 18500 |  |  | 10/02/2026 | Paid
Hemi Plumbing Ltd | Plumbing | 9429041234789 | INV-2087 | 10/02/2026 | 8950 |  |  | 20/02/2026 | Paid
Manaia Flooring Co | Flooring | 9429041235012 | INV-3311 | 25/02/2026 | 7600 |  |  | 05/03/2026 | Paid
Liam Painters | Painting | 9429041235298 | INV-4456 | 15/03/2026 | 6100 |  |  | 25/03/2026 | Paid
Charlotte Roofing NZ | Roofing | 9429041235654 | INV-5521 | 01/04/2026 | 16400 |  |  |  | Unpaid
Tane Electrical Ltd | Electrical | 9429041235987 | INV-6673 | 20/03/2026 | 5300 |  |  | 30/03/2026 | Paid
Hemi Plumbing Ltd | Plumbing | 9429041234789 | INV-2144 | 05/02/2026 | 3950 |  |  | 15/02/2026 | Paid
Nikau Windows Co | Joinery | 9429041236223 | INV-7789 | 05/04/2026 | 11200 |  |  |  | Unpaid
Sophie Landscapes | Landscaping | 9429041236559 | INV-8890 | 12/04/2026 | 8900 |  |  |  | Unpaid
TOTAL
Outstanding Invoices
Outstanding Amount (incl. GST)

## Dashboard
Renovation Budget Dashboard
Key Metric | Value
Total Budgeted Cost
Total Actual Cost
Total Variance
Percentage of Budget Spent
Total Contractor Invoices (incl. GST)
Outstanding Payments (incl. GST)
Category | Budgeted Cost | Actual Cost

## Instructions
How to Use This Workbook
Sheet | Guidance
Renovation Budget | Record every renovation category, room, contractor and cost. Enter Budgeted Cost and Actual Cost in the pale yellow cells. Variance, % of Total Budget and totals calculate automatically. Update Status using the dropdown list.
Contractor Payments | Track each contractor invoice, NZBN, GST and payment status. GST at 15% and the total incl. GST calculate automatically. Use the Payment Status dropdown to mark invoices as Paid, Unpaid or Part Paid.
Dashboard | View key metrics and charts summarising your renovation spend, including totals pulled automatically from the Renovation Budget and Contractor Payments sheets, plus a bar chart and pie chart of spend by category.
Editable Cells | Pale yellow cells (Budgeted Cost, Actual Cost, Invoice Amount) are meant to be edited. All other cells contain formulas and should not normally be overtyped.
GST | All GST calculations use the New Zealand standard rate of 15%. Confirm your contractor's GST/IRD number and NZBN before paying any invoice.
Currency | All amounts are shown in New Zealand Dollars (NZD) using the format $1,234.56.
Support | For renovation budgeting guidance, see the Building Performance and MBIE guidance at www.building.govt.nz, or consult a registered Quantity Surveyor.